## Test_Plan_Summary
Field | Value
Document ID | TP-PAY-UPI-IMPS-001
Document Title | Test Plan: Payment Module Validation (UPI & IMPS)
Version | 1
Prepared By | Test Lead
Date | 2026-04-04
Integration Partner | Razorpay (Sandbox Mode)
Platform Scope | Web Portal + Backend API Service
Payment Modes | UPI (Intent/Collect) + IMPS
Test Environment | Dedicated Staging with Data Masking
Test Data Source | Razorpay Sandbox Credentials + Synthetic Test Data
Compliance | PCI-DSS Data Masking + OWASP Security Guidelines

## Scope_Objectives
Category | Item | Details
In-Scope Components | Web Portal | Payment UI, UPI/IMPS selection, beneficiary form, status pages, error handling
In-Scope Components | Backend API | Order creation, payment initiation, status polling, webhook processing, refund APIs
In-Scope Flows | UPI | Successful payment, timeout handling, duplicate prevention, collect vs intent flow
In-Scope Flows | IMPS | Beneficiary validation, successful transfer, timeout/retry, duplicate prevention
In-Scope Common | Shared | Refund/reversal, webhook signature validation, data masking, audit logging
Out-of-Scope | Excluded | Load testing, other payment modes (Cards/Wallets), production validation, mobile apps
Test Objective 1 |  | Validate end-to-end successful payment flow for UPI & IMPS via Razorpay sandbox
Test Objective 2 |  | Verify transaction timeout handling with user feedback & reconciliation logic
Test Objective 3 |  | Ensure refund/reversal scenarios trigger correct state transitions & notifications
Test Objective 4 |  | Confirm duplicate transaction prevention via idempotency keys & order_id
Test Objective 5 |  | Validate IMPS beneficiary account verification (IFSC/account number) pre-transaction
Test Objective 6 |  | Ensure webhook signatures, payload integrity and idempotent processing
Test Objective 7 |  | Verify data masking for PII/PCI-sensitive fields in logs & UI

## Test_Strategy
Testing Type | Tools/Methods | Coverage Focus | Execution Mode
Functional Testing | Manual + Postman/Newman | UI workflows + API contracts + business rules | Manual + Automated
Integration Testing | Razorpay Sandbox + Mock Services | Webhook callbacks + bank simulator responses | Automated
Security Testing | OWASP ZAP + Manual Review | Data masking + HTTPS + signature validation | Manual + Tool-assisted
Negative/Edge Testing | Boundary value + fault injection | Timeout + network failure + invalid inputs | Manual
Regression Testing | Pytest/RestAssured + CI/CD | Critical paths post code changes | Automated
Test Design Technique | Application Area | Example
Equivalence Partitioning | Amount fields | Valid: 1-100000 | Invalid: 0/negative/>100000
Boundary Value Analysis | Transaction timeout | Test at 29s/30s/31s thresholds
State Transition Testing | Payment lifecycle | initiated → pending → success/failed/reversed
Decision Table Testing | Refund eligibility | Full/partial/refund-not-allowed scenarios
Error Guessing | Network failures | Simulate dropped connections during payment polling

## Environment_Data
Component | Configuration | Notes
Environment | Dedicated Staging | Mirrors production architecture
Frontend | Web Portal (Chrome/Firefox/Edge latest) | Responsive design validation
Backend | API Services (Node.js/Java) + Razorpay Sandbox | Health checks pre-execution
Database | Masked test DB with synthetic data | PCI-DSS compliant anonymization
Test Data - Razorpay | Test keys from Dashboard | Keep secrets in env variables
Test Data - UPI IDs | success@razorpay / timeout@razorpay / failure@razorpay | Per Razorpay docs
Test Data - IMPS | Mock beneficiaries (IFSC: HDFC0000001) | Pre-provisioned in staging DB
Data Masking Rule | Account Numbers | XXXX-XXXX-1234 format
Data Masking Rule | UPI IDs | test***@upi format
Data Masking Rule | Phone/Email | Partial masking per PCI-DSS guidelines
Data Masking Rule | Logs | Auto-redact via log4j/logback filters
Monitoring Tools | ELK Stack + Jaeger + Webhook Debugger | Real-time tracing & alerting

## Entry_Exit_Criteria
Criteria Type | Item | Status | Owner | Notes
ENTRY CRITERIA | Code freeze for payment module features | Not Executed | Dev Lead | Branch: release/pay-v1.0
ENTRY CRITERIA | Razorpay sandbox credentials configured | Not Executed | DevOps | Webhook URL validated
ENTRY CRITERIA | Test data provisioned & masked | Not Executed | QA Engineer | UPI IDs + IMPS beneficiaries ready
ENTRY CRITERIA | Staging environment smoke test passed | Not Executed | DevOps | All services healthy
ENTRY CRITERIA | Test cases reviewed & approved | Not Executed | Test Lead | Peer review completed
EXIT CRITERIA | 100% critical test cases executed | Not Executed | QA Lead | Traceability matrix attached
EXIT CRITERIA | Zero P1/P2 defects open | Not Executed | QA Lead | All critical bugs resolved & retested
EXIT CRITERIA | Webhook integration validated | Not Executed | SDET | Signature verification passed
EXIT CRITERIA | Test summary report signed off | Not Executed | Test Lead | Stakeholder approval received

## Risk_Mitigation
Risk Description | Impact Level | Probability | Overall Risk | Mitigation Strategy | Owner | Contingency Plan
Razorpay sandbox downtime | High | Medium | High | Maintain mock service fallback; schedule tests off-peak | DevOps | Switch to mock bank simulator
Incomplete webhook simulation | Medium | Medium | Medium | Use Razorpay webhook tester + custom mock server | SDET | Manual payload injection for edge cases
Data leakage in logs | Critical | Low | Medium | Enforce masking in log config; pre-commit PII scans | Security Lead | Audit logs pre-release; rotate credentials
Ambiguous timeout behavior | Medium | High | High | Define clear SLA (30-sec) with product; test network throttling | Test Lead | Document fallback behavior in runbook
Idempotency key collision | High | Low | Medium | Use UUIDv4 for order_id; validate uniqueness at API gateway | Backend Lead | Add DB unique constraint + retry logic

## Deliverables_Timeline
Deliverable | Owner | Start Date | End Date | Status | Dependencies
Test Plan (this document) | Test Lead | Day 1 | Day 1 | Approved | Requirements sign-off
Detailed Test Cases (Zephyr/Excel) | QA Engineers | Day 2 | Day 3 | In Prgoress | Test Plan approval
API Test Suite (Postman Collection) | SDET | Day 3 | Day 4 | Pending | Test case finalization
Test Data Setup Script | DevOps | Day 1 | Day 2 | Completed | Staging environment ready
Execution Report + Defect Dashboard | QA Lead | Daily | Daily | In Prgoress | Test execution started
Test Summary Report + Sign-off | Test Lead | Cycle End | Cycle End | Pending | Exit criteria met
Automation Framework Upgrade | SDET | Day 5 | Day 7 | Planned | CI/CD pipeline access

## Roles_Responsibilities
Role | Name (Optional) | Responsibilities | Contact
Test Lead |  | Plan ownership; risk mgmt; reporting; stakeholder comms; sign-off coordination | testlead@company.com
QA Engineers |  | Test case design; manual execution; defect logging; regression validation | qa-team@company.com
SDET |  | API automation; CI/CD integration; mock services; webhook testing | sdet@company.com
Backend Developer |  | Bug fixes; API contract adherence; idempotency implementation | backend-dev@company.com
DevOps Engineer |  | Environment provisioning; data masking setup; monitoring config | devops@company.com
Product Owner |  | Business rule clarification; UAT coordination; exit criteria approval | product@company.com
Security Specialist |  | PCI-DSS compliance review; log masking validation; penetration testing | security@company.com

## Approval_Signoff
Name | Role | Signature | Date | Comments
| Test Lead |  |  | Plan approved for execution
| Development Lead |  |  | Technical feasibility confirmed
| Product Owner |  |  | Business requirements validated
| Security Officer |  |  | PCI-DSS compliance verified
| QA Manager |  |  | Resource allocation approved